## Sheet1
Prepared by: Kyle Tran – Project manager of CC Project |  |  | Date: April 27th 2019
RISK REGISTER for CC Project
No | Risk | Reason | Category | Potential Respond | Risk Owner | Impact level | Proble level | Most critical risk
1 | Third-Party Specialist might have some conflicts with the contract of the company. This will cause the delay of the whole project. | Hiring third-party specialist will be harder to work with compared to the internal resource. The conflict in contract will delay the process because of the fast pace of CC project. | Negative risk | CEO & Project manager have to do quick respond to the third party to make clear everything in the contract again. The milestone, goal and budget might have to be extended. | Report reporter specialist | High | Medium | Yes
2 | Misunderstanding among managers when using online meeting instead of face to face meeting. | Sometimes the misunderstanding and conflicts occurs when people cannot read other people's emotion remotely. Online meeting or meeting through secretary might lead to conflicts and take more time to solve than traditional meeting. | Negative risk | Departments managers will write down the problem so the project manager and meeting master will discuss to solve in the training period. Milestone and deadline might have to extend. | Department managers | Medium | Medium | No
3 | The increasing in the number of tasks for team member who participate in replacement meeting program. | The increasing of tasks might annoy team members because they cannot get used to the system in a short amount of time. The fear of affecting their managers will be the discouragement. | Negative risk | The more training time and the bonus in salary will be the respond to get everyone into the new system. | Team members. | Low | High | No
4 | The new system might affects the structure/environment of the company. | Providing managers and team members flexibility equals to decreasing the power of CEO. This might lead to bad decision of the department manager, who cannot have the overview of the company. | Negative risk | If negative risk happened, CEO might interrupt the system and the flexible environment will be restricted again. | Department Managers | Medium | Medium | No
5 | Focusing on changing communication might delay the main project like Phoenix project for one to two weeks. | In order to get the managers and team members get used to new systems, this might take sometimes. Therefore, the main project will suffer from a delay. | Negative risk | The delay will discourage the CEO to continue the CC project in order to refocus on the Phoenix project. The CC project might suffer from interruption or cancellation. | Phoenix Project stakeholders, CEO. | Medium | High | Yes
6 | Hiring a third party to develop the report system & help with training will save a lot of time. The report system might be done ahead of the deadline | Having external human resources in focusing building new system will save a lot of time and resources for Parts Unlimited. The third party has experience and their own solution. Tailoring the solution to fit Parts Unlimited will save more time & energy than developing and testing a new one. | Positive risk | Reaching the deadline a head of time might save times for other tasks. The specialists can spend more time on training process of Parts Unlimited members. | Report reporter specialist | Medium | High | N/A
7 | Meeting master report urgent problem and hidden problem immediately to spot and solve unknown risks on time. | Giving the meeting masters permission to directly report to the CEO in urgent situation might help spot out unknown problem through meeting reports from the managers after every meetings. | Positive risk | The Parts Unlimited CEO & Project manager can immediately respond to the hidden problem. With the power of the CEO position, the direction to solve the conflict will be given to prevent future damage. | Meeting masters, CEO, Project Manager | High | Low | N/A