## Sheet1
Timeline for CC Project
Prepared by: Kyle Tran – Project manager of CC Project |  |  | Date: April 27th 2019
CC project or Change Communication project of Parts Unlimited will start from April 28th to May 26th. The project will include 5 main phases with an independent phase. Independent phases (or step 0) is the phase that run throughout the whole project.
Step | Task | Milestones
|  | Week1 |  | Week 2 |  | Week 3 |  | Week 4
0 | Having third party specialist building reporting system that constantly improves during the CC Project. |  | 1. Meeting with project manager. 2. Agreement of all milestones, goals and deliverables. 3.Detail planning for training programs. 4.Agreement of the new reporting system 5.and how to tailor the system for Parts Unlimited. |  | 1.Finishing the 1st draft for the new reporting system. 2. Start training Meeting masters with new system. | 1. Holding 1st training program for all managers with new reporting system. | 1. Finishing the 2nd draft for the new reporting system. 2. Finishing the training for meeting masters with new reporting system. | 1. Holding 2nd training program for all managers with new reporting system. | 1. Finishing the final product. 2. Having a final meeting with project manager to end contract. 3. Having an agreement on maintaining plan (if have) for the future.
1 | Having a meeting among CEO, department managers and project manager of CC Project to launch the CC Project. All the deliverables will be presented again for a final agreement. | 1. Agreement on all deliverables before launching CC Project. 2. Assign goals, plans and tasks for departments managers. 3. Introducing the third-party specialists for the development of new report system. 4. Answer all confusion and questions for the project.
2 | Publishing goal and the developing system for the whole Parts Unlimited. Seeking for trainee for replacement meeting training program and meeting master training program. Start training people for replacement meeting and meeting masters. |  | 1. Finding 2 Meeting masters & 3 trainees for replacement meeting training program from each departments. 2. Publish announcement on the training schedule, goals and tasks for people with new positions. | 1. Training meeting masters for new meeting system and how to work in this new organization structure. 2. Training the trainees for replacement meeting with duties, tasks and also the risks. 3. Answering all responds and questions of the trainees. 4. Schedule for practice meeting with departments managers in the following weeks. | 1. Meeting master starts training with the specialists. 2. Meeting masters starts applying the reporting method for the first practice meeting. 3. meeting masters finishing the reports for the online meeting. | 1. Trainees of the replacement meeting programs start participate in the 1st replacement meeting without departments managers. 2. Trainees of replacement meeting programs writes feedback, questions and suggestion for new method of meeting. 3.Meeting masters starts applying the reporting method for the 2nd practice meeting. | 1. Meeting master finishes the report system training program. 2.Meeting masters starts applying the reporting method for the 3rd practice meeting. 3. Trainees of the replacement meeting programs start participate in the 3rd replacement meeting with departments managers. 4. Trainees of replacement meeting programs writes feedback, questions and suggestion for new method of meeting. | 1. Trainees of the replacement meeting programs start participate in the 3rd replacement meeting with departments managers. 2. Trainees of replacement meeting programs writes feedback, questions and suggestion for new method of meeting. 3.Meeting masters starts applying the reporting method for the 4th practice meeting.
3 | Holding training for online meeting with departments managers. Having online meeting in the another half of the week to report disadvantage and adjust change to improve the system. |  |  | 1. Training for departments manager with online meeting system. | 1. Holding the practice online meeting 2. Receive feedbacks, question and suggestion for online meeting.
4 | Holding training for replacement meeting with departments managers. Having online meeting in the another half of the week to report disadvantage and adjust change to improve the system. |  |  |  |  | 1. Training for departments manager with replacement meeting system. | 1. Holding the 1st practice replacement meeting. 2. Receive feedbacks, question and suggestion for replacement meeting. | 1. Holding the 2nd practice replacement meeting. 2. Receive feedbacks, question and suggestion for replacement meeting.
5 | Final wrap up of the new reporting system. Final policy of new reporting system and new meeting system. | [7 empty] | 1. Final publishment of new meeting system and new reporting system in Parts Unlimited. 2. Creating a new policy for new systems. 3. Have the specialists and project manager answer the remaining questions and concerns of the stakeholders.